## 🚀 Pre-Flight Summary
CEIP — Pre-Flight Checklist ¦ Everything to prepare before opening Claude Code
Work through every sheet in order. Do NOT open Claude Code until every 🔴 Critical item is ✅ Done.
Category | Total Items | 🔴 Critical | Must Complete First | Sheet | Est. Time | Notes
1 · API Keys & Accounts | 9 items | 5 | CORE, IUCN, OpenAlex, GBIF, Semantic Scholar | 🔑 API Keys | ~2 hours | Some keys take 24–48h to activate — do these FIRST
2 · Software Installations | 7 items | 4 | Ollama, Python 3.11, Git, Node.js, Claude Code CLI | 💻 Software | ~45 mins | Ollama is macOS native — fast install
3 · Ollama Models | 2 items | 2 | gemma4:e4b (~6GB), nomic-embed-text (~500MB) | 🤖 AI Models | ~30 mins | Download overnight if on slow connection
4 · Python Libraries | 18 items | 6 | pydantic, langchain, chromadb, fastapi, sqlalchemy | 🐍 Python Libs | ~15 mins | One pip install command — see sheet
5 · Data Downloads | 5 items | 3 | Conservation Evidence CSV, IUCN bulk, WDPA | 📦 Datasets | ~2 hours | CE CSV is manual download from website
6 · Accounts & Platforms | 8 items | 3 | GitHub, Groq (free LLM), Hugging Face | 🌐 Accounts | ~30 mins | All free — needed for cloud deployment
7 · Project Setup | 7 items | 7 | Folder structure, .env, .gitignore, venv | 📁 Project Files | ~20 mins | The exact structure Claude Code expects
8 · Manual Preparations | 5 items | 5 | 20-question eval dataset, Pydantic contracts file | 📝 Manual Prep | ~4 hours | Most important — do NOT skip the eval dataset
9 · Claude Code Configuration | 4 items | 4 | Install CLI, CLAUDE.md project file, test run | 🤖 Claude Code | ~20 mins | CLAUDE.md gives Claude Code full project context
HOW TO USE THIS FILE 1. Start with sheet '🔑 API Keys' — register for all APIs today since some take 48h to approve. 2. Work through each sheet in order, marking items ✅ Done as you go. 3. The '🤖 Claude Code' sheet is the final gate — only open Claude Code once everything else is done. 4. The '📝 Manual Prep' sheet contains the most important work: your 20-question eval dataset and Pydantic contracts. These take ~4 hours but are the foundation the entire platform is built on. 5. Keep this file open during development as your running status tracker.

## 🔑 API Keys
🔑 API KEYS & ACCOUNTS — Register for these TODAY. Some take 24–48h to approve.
After getting each key, add it to your .env file immediately. NEVER put keys in code files or commit them to Git.
# | Service | What It's For in CEIP | Registration URL | Auth Type | Where to Store Key | Approval Time | Priority | Status
1 | CORE API | PRIMARY literature source — search & download 200M+ open-access conservation papers with full text | core.ac.uk/services/api | Bearer Token in Authorization header | CORE_API_KEY in .env | Instant | 🔴 Critical | ⬜ TODO
2 | IUCN Red List API | Species threat categories, conservation actions, habitat data for 172,600+ species | apiv3.iucnredlist.org → Login → Generate Token | ?token=YOUR_KEY param | IUCN_API_KEY in .env | 1–5 days (manual approval) | 🔴 Critical | ⬜ TODO
3 | OpenAlex API | 250M+ scholarly works — metadata, citations, concepts, abstracts. Powers the weekly living agent. | No registration needed. Add ?mailto=your@email for polite pool (10x rate limit) | Email param only (no key) | OPENALEX_EMAIL in .env | Instant — no approval | 🔴 Critical | ⬜ TODO
4 | GBIF API | 2.8B+ species occurrence records. Needed for species location data and bulk downloads. | gbif.org → Create Account (free) | Username + Password for downloads | GBIF_USER and GBIF_PASSWORD in .env | Instant | 🟡 High | ⬜ TODO
5 | Semantic Scholar API | 200M+ papers with citation graph & S2 semantic embeddings. Supplements CORE. | api.semanticscholar.org/product/api | Optional API key (higher rate limits) | S2_API_KEY in .env | Instant | 🟡 High | ⬜ TODO
6 | Protected Planet API | 312,000+ global protected areas — needed for location context and TNFD reporting module | api.protectedplanet.net → Register | API Token in header | PP_API_KEY in .env | 1–3 days | 🟡 High | ⬜ TODO
7 | CrossRef API | Resolve DOIs, retrieve full citation metadata for 130M+ papers. Used for source validation. | No registration. Add ?mailto=your@email | Email param only | CROSSREF_EMAIL in .env | Instant — no approval | 🟢 Medium | ⬜ TODO
8 | Groq API (free tier) | CLOUD LLM — replaces Ollama when deploying to Streamlit/cloud. Free tier: very fast. | console.groq.com → Sign Up → Create API Key | Bearer Token | GROQ_API_KEY in .env | Instant | 🔴 Critical | ⬜ TODO
9 | Hugging Face | Alternative cloud LLM + model downloads. Free tier for inference API. Needed for gemma4 weights. | huggingface.co → Sign Up → Settings → Access Tokens | Bearer Token | HF_TOKEN in .env | Instant | 🟡 High | ⬜ TODO
📋 YOUR .env FILE TEMPLATE — Copy this, fill in your keys, save as '.env' in the ceip/ root folder
# CEIP Environment Variables — DO NOT COMMIT THIS FILE
# Add .env to .gitignore immediately
# Literature APIs
CORE_API_KEY=bW4DckwaxK3Fnmh0U2Lpiy568ftvGgHY
OPENALEX_EMAIL=zakhbour@gmail.com
OPENALEX_API KEY= SmHpcxmfj9SBLcRtU2kZ4b
S2_API_KEY=RTRQ45E3Vo5AXw92lslil9mpahkuteGq5EQRJRfV
CROSSREF_EMAIL=your@email.com
# Biodiversity APIs
IUCN_API_KEY=jQseo1PACVhFvNwa6i3TZLtWbsH9RSEtuWQa
GBIF_USER=zakher
GBIF_PASSWORD=Samsung2038.
PP_API_KEY=your_protectedplanet_key
# AI / LLM
OLLAMA_BASE=http://localhost:11434
GROQ_API_KEY=your_groq_key_here
HF_TOKEN=your_huggingface_token_here
LLM_BACKEND=ollama # switch to 'groq' for cloud deployment
# Database & Storage
DB_PATH=data/ceip.db
CHROMA_PATH=data/embeddings/

## 💻 Software
💻 SOFTWARE INSTALLATIONS — Run every command in macOS Terminal (not Antigravity)
# | Software | Why You Need It | Install Command (macOS Terminal) | Verify Command | Priority | Status
1 | Homebrew | macOS package manager — needed to install many dev tools cleanly | /bin/bash -c "$(curl -fsSL https://raw.githubusercontent.com/Homebrew/install/HEAD/install.sh)" | brew --version | 🔴 Critical | ⬜ TODO
2 | Python 3.11 | Core language. Must be 3.11+ for Pydantic v2 and modern type hints. | brew install python@3.11 (or download from python.org) | python3.11 --version | 🔴 Critical | ⬜ TODO
3 | Git | Version control — essential for tracking changes and deploying to Streamlit Cloud | brew install git | git --version | 🔴 Critical | ⬜ TODO
4 | Ollama | Runs Gemma 4 E4B and nomic-embed-text locally on your M1 Pro via Metal GPU. FREE. | curl -fsSL https://ollama.com/install.sh ¦ sh | ollama --version | 🔴 Critical | ⬜ TODO
5 | Node.js + npm | Needed only for the docx npm package (used if you generate Word documents from the platform) | brew install node | node --version && npm --version | 🟡 High | ⬜ TODO
6 | Claude Code CLI | Your AI development assistant. Reads your entire codebase and helps you build each phase. | npm install -g @anthropic-ai/claude-code | claude --version | 🔴 Critical | ⬜ TODO
7 | Visual Studio Code (optional) | Alternative editor if Antigravity is slow. Open source, free, excellent Python support. | brew install --cask visual-studio-code | code --version | 🟢 Medium | ⬜ TODO

## 🤖 AI Models
🤖 OLLAMA MODEL DOWNLOADS — Run after Ollama is installed. Can run overnight.
M1 Pro 16GB: both models fit easily. Ollama uses Metal GPU automatically — no configuration needed.
Model | Pull Command | Size on Disk | RAM Used | Role in CEIP | Priority | Status
nomic-embed-text | ollama pull nomic-embed-text | ~500 MB | ~500 MB RAM | EMBEDDINGS ONLY — converts all papers, abstracts and queries to 768-dim vectors for ChromaDB. Does NOT generate text. This is the workhorse of the search system — runs thousands of times during Phase 3. | 🔴 Critical | ⬜ TODO
gemma4:e4b | ollama pull gemma4:e4b (check exact tag at ollama.com/library/gemma4) | ~5–6 GB | ~6–8 GB RAM | PRIMARY GENERATION MODEL — synthesises evidence, classifies papers, generates TNFD reports. Replaces llama3.2 + phi3 + llava. Native JSON mode, 128K context, multimodal, Apache 2.0. Google DeepMind, released April 2026. | 🔴 Critical | ⬜ TODO
gemma4:e2b (optional backup) | ollama pull gemma4:e2b | ~2–3 GB | ~3–4 GB RAM | FALLBACK — use if E4B is too slow during heavy batch classification. Lower quality than E4B for complex synthesis but faster for high-volume simple tasks like paper classification. | 🟢 Medium | ⬜ TODO
▶ AFTER PULLING BOTH MODELS — Run these verification commands in Terminal
Check models are listed | ollama list | Should show both nomic-embed-text and gemma4:e4b in the list | ⚠️ If gemma4:e4b tag doesn't work: Check ollama.com/library/gemma4 for the exact current tag name. Gemma 4 was released April 2026 — Ollama tag naming may have settled as 'gemma4:4b' or 'gemma4' (default) since release. The model itself will not change — only the Ollama tag name.
Test Gemma 4 generation | ollama run gemma4:e4b "In one sentence, what is conservation effectiveness?" | Should return a coherent 1-sentence answer within 15 seconds
Test embeddings (returns 768 numbers) | curl http://localhost:11434/api/embeddings -d '{"model":"nomic-embed-text","prompt":"test"}' | Should return: {"embedding": [0.123, -0.456, ...]} with 768 numbers
Confirm Metal GPU is active | ollama ps (while a model is running) | Should show GPU usage — confirms Metal acceleration is active on M1

## 🐍 Python Libs
🐍 PYTHON LIBRARIES — Run the master install command, then verify each library
MASTER INSTALL COMMAND (run once in Terminal, inside your activated venv): pip install pydantic requests httpx python-dotenv sqlalchemy pandas tqdm loguru beautifulsoup4 lxml openpyxl jupyter rapidfuzz chromadb langchain langchain-community langchain-ollama langchain-groq langchain-huggingface streamlit fastapi uvicorn sentence-transformers pymupdf geopandas
Library | pip install | Phase First Needed | Role in CEIP | Key Classes / Functions | Priority | Status
pydantic | pip install pydantic | Phase 0 | Defines all output contracts — enforces that AI always returns structured, validated data | BaseModel, Field, field_validator, ValidationError | 🔴 Critical | ⬜ TODO
python-dotenv | pip install python-dotenv | Phase 0 | Loads API keys from .env file safely — never hardcode keys in source | load_dotenv(), os.getenv() | 🔴 Critical | ⬜ TODO
sqlalchemy | pip install sqlalchemy | Phase 1 | ORM for SQLite database — all species, papers, interventions, users stored here | create_engine(), Session(), declarative_base() | 🔴 Critical | ⬜ TODO
pandas | pip install pandas | Phase 1 | Load and clean all CSV datasets (Conservation Evidence, IUCN, WDPA) | pd.read_csv(), .merge(), .groupby(), .to_sql() | 🔴 Critical | ⬜ TODO
requests | pip install requests | Phase 0 | Call all external APIs (CORE, IUCN, Ollama localhost) | requests.get(), .post(), .json() | 🔴 Critical | ⬜ TODO
httpx | pip install httpx | Phase 2 | Async HTTP for living data agent — fetch many papers in parallel quickly | httpx.AsyncClient(), await .get() | 🟡 High | ⬜ TODO
loguru | pip install loguru | Phase 0 | Structured logging — essential for debugging long-running data pipelines | logger.info(), .warning(), .error() | 🟡 High | ⬜ TODO
tqdm | pip install tqdm | Phase 1 | Progress bars for long jobs (embedding 45,000 chunks, fetching 20,000 papers) | for x in tqdm(items): ... | 🟡 High | ⬜ TODO
rapidfuzz | pip install rapidfuzz | Phase 1 | Fuzzy string matching — links IUCN conservation actions to CE interventions | fuzz.token_sort_ratio() | 🟡 High | ⬜ TODO
chromadb | pip install chromadb | Phase 3 | Local vector database — stores 40,000+ document embeddings for semantic search | PersistentClient(), .create_collection(), .add(), .query() | 🔴 Critical | ⬜ TODO
langchain | pip install langchain langchain-community | Phase 3 | RAG orchestration — document splitting, retrieval chains, ensemble retriever | RecursiveCharacterTextSplitter, EnsembleRetriever, RetrievalQA | 🔴 Critical | ⬜ TODO
langchain-ollama | pip install langchain-ollama | Phase 4 | Connects LangChain to local Ollama — OllamaLLM and OllamaEmbeddings classes | OllamaLLM(model='gemma4:e4b'), OllamaEmbeddings() | 🔴 Critical | ⬜ TODO
langchain-groq | pip install langchain-groq | Phase 5 | Cloud LLM backend swap — replace Ollama with Groq for deployed cloud app | ChatGroq(model='gemma2-9b-it') | 🟡 High | ⬜ TODO
streamlit | pip install streamlit | Phase 6 | Build the entire MVP web interface in pure Python — no HTML/CSS/JS needed | st.text_input(), st.write(), st.chat_input(), st.button() | 🟡 High | ⬜ TODO
fastapi | pip install fastapi uvicorn | Phase 5 | Production REST API backend serving all platform endpoints | @app.get(), @app.post(), BaseModel, JSONResponse | 🟡 High | ⬜ TODO
pymupdf | pip install pymupdf | Phase 3 | Extract text from conservation paper PDFs when abstract-only is insufficient | fitz.open(), page.get_text() | 🟢 Medium | ⬜ TODO
geopandas | pip install geopandas | Phase 5 | Work with WDPA protected area shapefiles for TNFD location-based reporting | gpd.read_file(), .sjoin(), .to_crs() | 🟢 Medium | ⬜ TODO
sentence-transformers | pip install sentence-transformers | Phase 3 | Access SPECTER2 model — best embedding model for scientific papers (alternative to nomic) | SentenceTransformer('allenai-specter'), .encode() | 🟢 Medium | ⬜ TODO

## 📦 Datasets
📦 DATA DOWNLOADS — You own these datasets. Download and store in ceip/data/raw/
These are NOT API calls — these are one-time manual downloads. Store them in ceip/data/raw/ and NEVER commit to Git (add data/ to .gitignore).
# | Dataset | Download URL / Instructions | File Format | Approx Size | Where to Store | Phase Needed | Priority | Status
1 | Conservation Evidence Database | 1. Go to: conservationevidence.com/content/page/79 2. Click 'Download the data' 3. You get a CSV of all 3,891 interventions with CE effectiveness scores. This is your most important dataset — the core of the platform. | CSV | ~50 MB | data/raw/conservation_evidence.csv | Phase 1 | 🔴 Critical | ⬜ TODO
2 | IUCN Red List (bulk download) | 1. Go to: iucnredlist.org/resources/grid 2. Register for an account if needed 3. Request bulk data download (assessments + habitats + threats + actions) Note: may take 1–2 days to receive download link by email | CSV + Shapefiles | ~5 GB | data/raw/iucn/ | Phase 1 | 🔴 Critical | ⬜ TODO
3 | WDPA Protected Areas | 1. Go to: protectedplanet.net/en/thematic-areas/wdpa 2. Click 'Download' → choose Monthly Release 3. Select: Global GeoPackage or Shapefile Start with CSV-only option for Phase 1 (much smaller) | GeoPackage / CSV / SHP | ~1.5 GB (full) / ~200 MB (CSV only) | data/raw/wdpa/ | Phase 1 | 🟡 High | ⬜ TODO
4 | PREDICTS Database | 1. Go to: nhm.ac.uk → Data Portal → search 'PREDICTS' 2. Download: 'The PREDICTS database: a global database of local responses' 3. Requires free registration on NHM Data Portal | CSV | ~500 MB | data/raw/predicts.csv | Phase 3 | 🟡 High | ⬜ TODO
5 | Conservation Evidence Journal articles | 1. Go to: conservationevidencejournal.com 2. Browse and download open-access PDF articles 3. These supplement the CSV with narrative evidence Focus on synopses most relevant to your initial taxa focus | PDF | Variable (~2–10 GB) | data/raw/ce_pdfs/ | Phase 3 | 🟢 Medium | ⬜ TODO

## 🌐 Accounts
🌐 PLATFORM ACCOUNTS — Create these for deployment, hosting and version control. All free.
# | Platform | Why You Need It | Sign Up URL | What to Do After Signing Up | Priority | Status
1 | GitHub | Version control for all CEIP code. Needed for Streamlit Cloud deployment and collaboration. | github.com → Sign Up | Create new private repo named 'ceip'. Add SSH key from your Mac. Create .gitignore. | 🔴 Critical | ⬜ TODO
2 | Streamlit Community Cloud | Free deployment for your Streamlit MVP app. Public URL for beta users. | share.streamlit.io → Sign in with GitHub | Connect your ceip GitHub repo. Set secrets (API keys) in the dashboard. No credit card. | 🔴 Critical | ⬜ TODO
3 | Groq Cloud (free tier) | Very fast free LLM API — replaces Ollama for cloud-deployed app. No credit card for free tier. | console.groq.com → Sign Up | Create API key. Add GROQ_API_KEY to your .env and to Streamlit Cloud secrets. | 🔴 Critical | ⬜ TODO
4 | Hugging Face | Download Gemma 4 model weights if needed. Free inference API as cloud LLM backup. | huggingface.co → Sign Up | Create access token (Settings → Access Tokens → New Token, type: Read). Store as HF_TOKEN. | 🟡 High | ⬜ TODO
5 | Render.com (free tier) | Alternative cloud host for FastAPI backend. Better than Streamlit for API endpoints. | render.com → Sign Up with GitHub | Connect GitHub repo. Will be used in Phase 5 to deploy FastAPI backend. | 🟡 High | ⬜ TODO
6 | Supabase (free tier) | Managed PostgreSQL + pgvector — upgrade path from local SQLite/ChromaDB when you scale. | supabase.com → Start for free | Create project. Note connection string. Not needed until Phase 7 scaling. | 🟢 Medium | ⬜ TODO
7 | WILDLABS.NET | Conservation technology community — post here to recruit beta users in Phase 6. | wildlabs.net → Join | Complete your profile. Join the 'AI for Conservation' working group. Post when ready for beta. | 🟡 High | ⬜ TODO
8 | LinkedIn (if not already active) | Post about CEIP to attract beta users, partners, and funders. Required for outreach. | linkedin.com | Ensure your profile shows conservation + AI background. Connect with conservation networks. | 🟢 Medium | ⬜ TODO

## 📁 Project Setup
📁 PROJECT FILE SETUP — Run these commands in Terminal to create the exact structure Claude Code expects
# | Action | Command / Content | File Path | Why It Matters | Priority | Status
1 | Create project folder | mkdir ceip && cd ceip | ~/ceip/ | All CEIP code lives here. Use this as your root for Claude Code. | 🔴 Critical | ⬜ TODO
2 | Create full folder structure | mkdir -p contracts eval data/raw data/processed data/embeddings src/intelligence src/living src/application src/api app tests notebooks | ceip/ (see Implementation Plan Phase 0) | Separates concerns cleanly. Claude Code will reference these paths throughout. | 🔴 Critical | ⬜ TODO
3 | Create virtual environment | python3.11 -m venv venv && source venv/bin/activate | ceip/venv/ | Isolated Python environment — prevents library version conflicts. | 🔴 Critical | ⬜ TODO
4 | Create .gitignore | echo '.env venv/ data/raw/ data/embeddings/ __pycache__/ *.pyc .DS_Store' > .gitignore | ceip/.gitignore | Prevents API keys and large data files from being committed to GitHub. | 🔴 Critical | ⬜ TODO
5 | Create .env file (empty template) | touch .env (then fill in your keys from the API Keys sheet) | ceip/.env | Stores all secrets. Never commit. Add to .gitignore immediately. | 🔴 Critical | ⬜ TODO
6 | Initialise Git repo | git init && git add .gitignore && git commit -m 'Initial commit' | ceip/.git/ | Start version control from day one. Push to GitHub after first commit. | 🔴 Critical | ⬜ TODO
7 | Create requirements.txt | pip freeze > requirements.txt (run after installing all libraries from Python Libs sheet) | ceip/requirements.txt | Pins all library versions. Needed for Streamlit Cloud deployment. | 🟡 High | ⬜ TODO

## 📝 Manual Prep
📝 MANUAL PREPARATIONS — The most important work. Cannot be automated. Budget ~4–5 hours.
These 5 items must be done by hand — they require your domain knowledge. They are the foundation everything else is built on. Do not skip or rush the eval dataset.
# | Item | What to Do — Step by Step | Output File Path | Time Estimate | Priority | Status
1 | 20-Question Gold Evaluation Dataset | 1. Open conservationevidence.com and browse synopses. 2. Pick 20 questions with known CE answers — one per intervention type/taxa combination. 3. For each: write question, expected_intervention, expected_ce_category, expected_outcome_direction, expected_confidence, species_group, geography, ce_synopsis. 4. Cover: mammals, birds, fish, invertebrates, plants, marine, freshwater, forest, 5+ intervention types, 6+ countries. 5. Have 1 conservation colleague verify your 20 answers are correct. FORMAT: JSON array. See Implementation Plan Phase 0 Step 3 for exact schema. | eval/gold_dataset.json | 3–4 hours | 🔴 Critical | ⬜ TODO
2 | Pydantic Output Contracts File | 1. Create: contracts/evidence.py 2. Define these classes exactly as shown in Phase 0 Step 2 of the Implementation Plan: - EvidenceStrength (Enum: strong/moderate/weak/none) - Citation (BaseModel: index, paper_id, title, year, source) - Intervention (BaseModel: name, ce_category, effectiveness_pct, n_studies, outcome_direction) - EvidenceSynthesis (BaseModel: answer, confidence, interventions, evidence_gaps, citations, geo_limits, taxa_limits) 3. Add field_validator to EvidenceSynthesis that rejects answers under 20 words. 4. Test: run python contracts/evidence.py — should import with no errors. | contracts/evidence.py | 45 mins | 🔴 Critical | ⬜ TODO
3 | CLAUDE.md Project Context File | 1. Create: ceip/CLAUDE.md (Claude Code reads this automatically on startup) 2. Include: project name, architecture summary, folder structure explanation, tech stack (Ollama + Gemma 4 E4B + nomic-embed-text + ChromaDB + SQLite + FastAPI + Streamlit), Pydantic contracts location (contracts/), eval dataset location (eval/), .env variables list, current phase, and any conventions you want Claude Code to follow. 3. This file is your 'briefing document' for every Claude Code session. The better it is, the faster Claude Code can help you. 4. Update it at the end of each phase with what was built. | ceip/CLAUDE.md | 30 mins | 🔴 Critical | ⬜ TODO
4 | Conservation Evidence Taxonomy Map | 1. Open the CE CSV you downloaded. 2. List all unique values in: synopsis_title, effectiveness_category columns. 3. Create a simple JSON map: which synopsis titles correspond to which taxa groups (birds, mammals, fish, etc.) and which habitat types. 4. This map is used by the classifier and TNFD module to categorise evidence correctly. 5. Example: {'Bird Conservation': {'taxa': 'birds', 'habitat': 'multiple'}, ...} | data/processed/ce_taxonomy_map.json | 30 mins | 🔴 Critical | ⬜ TODO
5 | Hardware Verification Run | 1. With Ollama running and gemma4:e4b pulled, run a test synthesis: Ask Gemma 4 to summarise a 500-word conservation abstract and return JSON. 2. Measure time: should be <30 seconds on M1 Pro. 3. Check Activity Monitor: confirm Ollama is using GPU, not just CPU. 4. Run embedding: embed 100 text chunks with nomic-embed-text, confirm all 768-dim. 5. Document your actual speeds — this sets realistic expectations for Phase 3 batch embedding. | tests/t0_hardware_baseline.txt (record timings here) | 30 mins | 🔴 Critical | ⬜ TODO

## 🤖 Claude Code
🤖 CLAUDE CODE SETUP — The final gate. Complete ALL previous sheets before this one.
Once you open Claude Code and point it at your ceip/ folder, you are building. Everything below must be ready.
# | Step | What to Do | Command | Expected Result | Priority | Status
1 | Install Claude Code CLI | Install the Claude Code command-line tool globally via npm. | npm install -g @anthropic-ai/claude-code | claude --version returns a version number | 🔴 Critical | ⬜ TODO
2 | Verify Claude Pro subscription | Claude Code requires a Claude Pro subscription. Confirm your subscription is active at claude.ai/settings. | Open claude.ai → Settings → Subscription | Status shows 'Pro' or 'Max'. If not, upgrade before proceeding. | 🔴 Critical | ⬜ TODO
3 | First Claude Code session | Navigate to your ceip/ folder in Terminal and start Claude Code. It will read your CLAUDE.md automatically and know the full project context. | cd ~/ceip && claude | Claude Code shows your project context from CLAUDE.md and is ready for instructions. | 🔴 Critical | ⬜ TODO
4 | Test first Phase 0 command | In Claude Code, give this exact instruction to verify it understands the project: 'Based on the CLAUDE.md, write the complete src/db.py file with all SQLAlchemy models for Phase 1: Paper, Intervention, Species, and SpeciesInterventionLink tables. Use the column names from the Implementation Plan.' | (Type in Claude Code terminal) | Claude Code creates src/db.py with correct SQLAlchemy models. If it asks clarifying questions about the schema, your CLAUDE.md is incomplete — update it. | 🔴 Critical | ⬜ TODO
📋 CLAUDE.md TEMPLATE — Create this file at ceip/CLAUDE.md before your first Claude Code session
# CEIP — Conservation Effectiveness Intelligence Platform
## What this project is
A SaaS platform that combines a living conservation evidence database with AI-powered synthesis.
Practitioners ask natural-language questions about what conservation interventions work.
The platform returns cited, structured answers updated weekly by an autonomous ingestion agent.
Users never see the pipeline — they see a clean web interface.
## Architecture (build bottom-up in this order)
1. Intelligence Layer: RAG engine, Gemma 4 E4B, ChromaDB, SQLite, Pydantic contracts
2. Living Data Layer: Weekly autonomous agent (OpenAlex API), relevance classifier, ChromaDB feeder
3. Application Layer: FastAPI backend, user accounts, project registry, alerts, TNFD module
4. User Interface: Streamlit MVP, then React production
## Tech Stack
- IDE: Antigravity (Google) + Claude Code CLI
- Language: Python 3.11
- LLM (local): Ollama + Gemma 4 E4B (ollama pull gemma4:e4b)
- Embeddings: nomic-embed-text via Ollama (768 dimensions)
- LLM (cloud/deploy): Groq API (LLM_BACKEND=groq env variable)
- Vector DB: ChromaDB persistent (data/embeddings/)
- Structured DB: SQLite → PostgreSQL at scale (data/ceip.db)
- RAG Framework: LangChain + Pydantic v2 contracts
- Web UI: Streamlit (MVP), FastAPI (backend)
- Hardware: Mac M1 Pro 16GB unified memory
## Key Files
- contracts/evidence.py: All Pydantic output schemas — NEVER bypass these
- eval/gold_dataset.json: 20-question benchmark — run after every major change
- .env: All API keys (CORE_API_KEY, IUCN_API_KEY, GROQ_API_KEY, etc.)
- data/raw/: Downloaded datasets — never commit these
- data/embeddings/: ChromaDB storage — never commit these
## Harness-First Rules (IMPORTANT)
1. ALL AI outputs must conform to contracts/evidence.py EvidenceSynthesis schema
2. Always use format='json' with Gemma 4 for structured extraction
3. Temperature = 0.05 for evidence synthesis (near-deterministic)
4. Every AI call has retry logic (max 3 attempts) + safe_fallback_response()
5. Run eval/gold_dataset.json benchmark after any model/prompt/retrieval change
6. Log every query: query_type, n_chunks, confidence, validation_passed, latency_ms
## Current Phase
Phase 0 — Environment setup. Building: database schema, Pydantic contracts, eval dataset.
## Conventions
- Use loguru for all logging (not print statements)
- Type hints on all functions
- Pydantic models for all API request/response schemas
- Never hardcode API keys — always os.getenv()

## ✅ Master Checklist
✅ MASTER CHECKLIST — Every single item before Claude Code. Print this and tick off.
# | Item | Category | Time | Priority | Status
1 | Register for CORE API key | API Keys | 5 min | 🔴 Critical | ⬜ TODO
2 | Request IUCN Red List API token | API Keys | 5 min | 🔴 Critical | ⬜ TODO
3 | Note OpenAlex email param (no key needed) | API Keys | 1 min | 🔴 Critical | ⬜ TODO
4 | Create GBIF account (username + password) | API Keys | 5 min | 🟡 High | ⬜ TODO
5 | Register Semantic Scholar API key | API Keys | 5 min | 🟡 High | ⬜ TODO
6 | Register Protected Planet API key | API Keys | 5 min | 🟡 High | ⬜ TODO
7 | Sign up for Groq API key (free) | API Keys | 5 min | 🔴 Critical | ⬜ TODO
8 | Create Hugging Face account + access token | API Keys | 5 min | 🟡 High | ⬜ TODO
9 | Create .env file with all keys | API Keys | 15 min | 🔴 Critical | ⬜ TODO
10 | Install Homebrew | Software | 5 min | 🔴 Critical | ⬜ TODO
11 | Install Python 3.11 | Software | 5 min | 🔴 Critical | ⬜ TODO
12 | Install Git | Software | 2 min | 🔴 Critical | ⬜ TODO
13 | Install Ollama | Software | 5 min | 🔴 Critical | ⬜ TODO
14 | Install Node.js + npm | Software | 5 min | 🟡 High | ⬜ TODO
15 | Install Claude Code CLI (npm install -g) | Software | 2 min | 🔴 Critical | ⬜ TODO
16 | ollama pull nomic-embed-text | AI Models | 5 min | 🔴 Critical | ⬜ TODO
17 | ollama pull gemma4:e4b | AI Models | 20 min | 🔴 Critical | ⬜ TODO
18 | Verify both models with test commands | AI Models | 5 min | 🔴 Critical | ⬜ TODO
19 | Create Python venv (python3.11 -m venv venv) | Python | 1 min | 🔴 Critical | ⬜ TODO
20 | Run master pip install command | Python | 10 min | 🔴 Critical | ⬜ TODO
21 | pip freeze > requirements.txt | Python | 1 min | 🟡 High | ⬜ TODO
22 | Download Conservation Evidence CSV | Datasets | 10 min | 🔴 Critical | ⬜ TODO
23 | Request IUCN bulk data download | Datasets | 10 min | 🔴 Critical | ⬜ TODO
24 | Download WDPA CSV (not shapefile for now) | Datasets | 15 min | 🟡 High | ⬜ TODO
25 | Download PREDICTS database | Datasets | 20 min | 🟡 High | ⬜ TODO
26 | Store all datasets in data/raw/ | Datasets | 5 min | 🔴 Critical | ⬜ TODO
27 | Create GitHub account + ceip repo | Accounts | 10 min | 🔴 Critical | ⬜ TODO
28 | Sign up Streamlit Community Cloud | Accounts | 5 min | 🔴 Critical | ⬜ TODO
29 | Sign up Render.com (free tier) | Accounts | 5 min | 🟡 High | ⬜ TODO
30 | Sign up Supabase (free tier) | Accounts | 5 min | 🟢 Medium | ⬜ TODO
31 | Join WILDLABS.NET | Accounts | 10 min | 🟡 High | ⬜ TODO
32 | Create ceip/ folder structure (all subfolders) | Setup | 5 min | 🔴 Critical | ⬜ TODO
33 | Create .gitignore (exclude .env and data/) | Setup | 2 min | 🔴 Critical | ⬜ TODO
34 | git init + first commit | Setup | 2 min | 🔴 Critical | ⬜ TODO
35 | Push to GitHub | Setup | 5 min | 🟡 High | ⬜ TODO
36 | Write 20-question eval dataset JSON | Manual Prep | 3–4 hrs | 🔴 Critical | ⬜ TODO
37 | Write Pydantic contracts (contracts/evidence.py) | Manual Prep | 45 min | 🔴 Critical | ⬜ TODO
38 | Create CLAUDE.md with full project context | Manual Prep | 30 min | 🔴 Critical | ⬜ TODO
39 | Create CE taxonomy map JSON | Manual Prep | 30 min | 🔴 Critical | ⬜ TODO
40 | Run hardware baseline verification | Manual Prep | 30 min | 🔴 Critical | ⬜ TODO
41 | Verify Claude Pro subscription active | Claude Code | 1 min | 🔴 Critical | ⬜ TODO
42 | Run: cd ~/ceip && claude | Claude Code | 1 min | 🔴 Critical | ⬜ TODO
43 | Confirm Claude Code reads CLAUDE.md | Claude Code | 2 min | 🔴 Critical | ⬜ TODO
44 | Run first test command (write src/db.py) | Claude Code | 5 min | 🔴 Critical | ⬜ TODO
TOTAL: 44 items ¦ Critical items: 32